## Info
Cycle Work Estimate
Sprint Data (2-Weeks)
Calendar-days | Actual work-days | Man-day/Point | Av. Point/Story | Hours/work-day
12 | 10 | 1 | 6 | 8
Sprint | Members | Work-days | Man-days | Max. Points | Est. Stories | Act. Points | Act. Stories
1 | 2 | 10 | 20 | 20 | 3
Date: Monday, 04/11/2019 - Saturday, 16/11/2019
Goal: SGB project
Stories: 3+
Velocity: 15+
Work days: 10 (0.8 * 12 calendar days)
Params: (days/point): 1, (point/story): 6
Schedule:
. Sprint planning: 9:00 - 12:00, 04/11/2019
. Daily scrum: 9:00 - 9:15
. Sprint review: 9:00 - 12:00, 16/11/2019
. Sprint retrospective: 15:00 - 17:00, 16/11/2019
Team: Tiến (SM), Hoang (Adviser)

## Story
| Total Story | Total Points
| 3 | 20 |  |  | 20 | 20 | 20 | 17 | 14 | 12 | 10 | 8 | 4 | 3 | 1 | 0 | 0 | 0
ID | Story | Estimate (points) | Acceptance Criteria | Member | Effort remaining (man-days)
[5 empty] | SUB | TOT | T2 | T3 | T4 | T5 | T6 | T7 | T2 | T3 | T4 | T5 | T6 | T7
7
2.01 | [As] a Developer [I want] to research about new framework for client and server | 6 | reorganize folder /framework | Hoang | 6 | 6 | 6 | 5 | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0
2.02 | [As] a Developer [I want] to develop a client/admin prototype for story: Registration | 10 | build folders /admin and /client | Tien | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 3 | 2 | 1 | 0 | 0 | 0
2.03 | [As] a Developer [I want] to design a database for SGB | 4 | design ERD for SGB: court booking, academy admin, and CBL admin | Hoang, Tien | 4 | 4 | 4 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## Burndown
Day | Burn Rate | Actual Rate | Show | Unit
T2 | 20 | 20 | * | 0
T3 | 18.1818 | 17 | * | 1
T4 | 16.3636 | 14 | * | 2
T5 | 14.5455 | 12 | * | 3
T6 | 12.7273 | 10 | * | 4
T7 | 10.9091 | 8 | * | 5
T2 | 9.0909 | 4 | * | 6
T3 | 7.2727 | 3 | * | 7
T4 | 5.4545 | 1 | * | 8
T5 | 3.6364 | 0 | * | 9
T6 | 1.8182 | 0 | * | 10
T7 | 0 | 0 | * | 11