## Info
Cycle Work Estimate
Sprint Data (2-Weeks)
Calendar-days | Actual work-days | Man-day/Point | Av. Point/Story | Hours/work-day
12 | 10 | 1 | 6 | 8
Sprint | Members | Work-days | Man-days | Max. Points | Est. Stories | Act. Points | Act. Stories
1 | 2 | 10 | 20 | 20 | 3
Date: Monday, 18/11/2019 - Saturday, 30/11/2019
Goal: SGB project
Stories: 3+
Velocity: 15+
Work days: 10 (0.8 * 12 calendar days)
Params: (days/point): 1, (point/story): 6
Schedule:
. Sprint planning: 9:00 - 12:00, 18/11/2019
. Daily scrum: 9:00 - 9:15
. Sprint review: 9:00 - 12:00, 30/11/2019
. Sprint retrospective: 15:00 - 17:00, 30/11/2019
Team: Tiến (SM), Hoang (Adviser)

## Story
| Total Story | Total Points
| 3 | 20 |  |  | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ID | Story | Estimate (points) | Acceptance Criteria | Member | Effort remaining (man-days)
[5 empty] | SUB | TOT | T2 | T3 | T4 | T5 | T6 | T7 | T2 | T3 | T4 | T5 | T6 | T7
7
1.01 | [As] a player [I want] to book a court and pay online | 8 | Hoang: client - Tien: server, DB - E2E screentshot | Hoang, Tien | 8 | 8 | T2: 8
1.02 | [As] an adminstrator [I want] to define prices by location for each booking session (30 minutes) | 6 | Tien: admin | Tien | 6 | 6 | T2: 6
1.03 | [As] an adminstrator [I want] to define peak and non-peak period, and prices by period | 6 | Tien: admin | Tien | 6 | 6 | T2: 6
1.04 | [As] an adminstrator [I want] to define which venue, and which time require a security deposit (credit card hold) |  | Sprint 3
1.05 | [As] an adminstrator [I want] to define block booking for court with no payment (include training session name) |  | Sprint 3
1.06 | [As] an adminstrator [I want] to view report on court booking |  | Sprint 3

## Burndown
Day | Burn Rate | Actual Rate | Show | Unit
T2 | 20 | 20 | * | 0
T3 | 18.1818 | #N/A |  | 1
T4 | 16.3636 | #N/A |  | 2
T5 | 14.5455 | #N/A |  | 3
T6 | 12.7273 | #N/A |  | 4
T7 | 10.9091 | #N/A |  | 5
T2 | 9.0909 | #N/A |  | 6
T3 | 7.2727 | #N/A |  | 7
T4 | 5.4545 | #N/A |  | 8
T5 | 3.6364 | #N/A |  | 9
T6 | 1.8182 | #N/A |  | 10
T7 | 0 | #N/A |  | 11