## BACKLOG
DATE | ID | PRIORITY | ESTIMATE | SPRINT # | TYPE | STORY | ACCEPTANCE CRITERIA | NOTE | MEMBER
2020-01-01 | 1.01 |  | 2 | 1 | RS | [As] a Developer [I want] to research about Agile Scrum | * What is Agile? * What is Scrum? * How does Scrum work? | Tien
2020-01-01 | 1.02 |  | 3 | 1 | RS | [As] a Developer [I want] to research about Git, Github | * What is Git? * What is Github? * What is Git-flow? * Repository, Clone, Commit, Push, Pull, Branch, Tag? * Install SourceTree | Tien
2020-01-01 | 1.03 |  | 5 | 1 | RS | [As] a Developer [I want] to research about Ionic3 (Angular 5, Cordova) | * Building Mobile Apps With Ionic: https://1drv.ms/b/s!Ao4U9J5NJW4xgqc7pQCm_Q4YVZctCQ?e=ZNjF03 * Quick Lists (page 216) * Develop on the web, build and run on Android/iOS real device | Tien
2020-01-01 | 1.05 |  |  | 2 | RS | [As] a Developer [I want] to research about PHP |  | Tien
2020-01-01 | 1.06 |  |  | 2 | RS | [As] a Developer [I want] to research about MySQL |  | Tien
2020-01-01 | 1.07 |  |  | 2 | RS | [As] a Developer [I want] to research about HTML, CSS, JS |  | Tien
2020-01-01 | 2.01 |  |  | 3 | RS | [As] a Developer [I want] to research about MVC and Framework | * Server * Admin Panel * Client App | Tien
2020-01-01 | 3.01 |  |  | 3 | RS | [As] a Developer [I want] to run Training project | * Clone project from github * Import database (database/training.sql) * Run Admin Panel (Email: info@sgbasketball.com ¦ Password: 12345) * Add new user with role is Administrator * Run Client App on Android/iOS (Email: trainee@gmail.com ¦ Password: 12345) * Add new booking | Tien
2020-01-01 | 3.02 |  |  | 3 | RS | [As] a Developer [I want] to research about Datatables and Editor | - Create Tables > Locations to view and create/edit/delete locations - Create table Courts is child row (https://datatables.net/examples/api/row_details.html) of Locations to view and create/edit/delete courts by location | Tien
2020-01-01 | 3.03 |  |  | 3 | RS | [As] a Developer [I want] to update Court Booking process | Step 1: Select Court Booking in home page Step 2: Click "New booking" to open Locations page Step 3: Select location and click "Next" to open Court Type page Step 4: Select court type and click "Next" to open Datetime page Step 5: Select court, date, time and click "Book Now" to open Payment page Step 6: Click "Pay Now" to confirm payment and finish booking | Tien
2020-01-01 | 3.04 |  |  | 3 | RS | [As] a Developer [I want] to create Bookings module on Admin Panel [so] can see all bookings | - Create Bookings module on the left menu - Bookings page will show all court bookings and details | Tien
2020-01-01 | 4.01 |  |  | 4 | RS | [As] a Developer [I want] to building ionic app for Android and Distributing to Google Play |  | Tien
2020-01-01 | 4.02 |  |  | 4 | RS | [As] a Developer [I want] to building Ionic app for iOS and Distributing to the Apple App Store |  | Tien
2020-01-01 | 4.03 |  |  | 4 | RS | [As] a Developer [I want] to research about Google Cloud Platform |  | Tien
2020-01-01 | 4.04 |  |  | 4 | RS | [As] a Developer [I want] to research about File Transfer Protocol (FTP) |  | Tien
2020-01-01 | 5.01 |  |  | 5 | RS | [As] a Developer [I want] to test client app | * TDD * 2E2 | Tien